## Summary
Regional Engagement Team - Summary progress
Objectives/goals: Helping testing to be more demand led by communicating the testing options to Directors of Public Health Communicating testing demands and requirements to channel teams to fulfill demands Communicating requests to make helpful adjustements to testing approaches to prototype team to improve accessibility to Antigen testing Enable Directors of Public Health and local authorities to select and target local testing activities so they are tailored to local communities and populations, especially hard-to-reach and vulnerable people. Support establishment of a process for planning and flexibly fulfilling testing capacity across the UK.
Regional Engagement
Regional Engagement Leads have been engaging with the relevant stakeholders at a regional level to support ongoing localisation efforts. This includes regular meetings with Senior Regional Coordinators, and the DPH Network to discuss testing options and ongoing progress.
Summary totals |  |  | Comments
Total Regional Conveners engaged | 9 | 100% | Introductory calls held with each Regional Convener; ways of working agreed, and coordination is being delivered at the SRC level.
Total Regional Coordinators engaged | 9 | 100% | Regional Engagement Leads and Senior Regional Coordinators/Regional Coordinators working in tandem on Local Authority Engagement. RELs have engaged and established weekly checkpoints with SRCs that cover progress, upcoming actions, and updates on relevant information. This is in addition to new meetings scheduled with Local Authorities, that are co-run by the SRC and Regional Engagement Lead.
Total DPHs engaged | 153 | 100% | Regional Engagement team has been introduced at the Fortnightly DPH Forum (National), and have shared the testing options pack to every DPH. Additionally, [Name Redacted] presented to the East of England DPH Forum on 17/07, covering some upcoming localisation activities and how they can support. Further engagement is scheduled with DPHs from across the sub-regions of London (North East, North West, South East, South West) over the next two weeks. | Regional Engagement team has been introduced at the Fortnightly DPH Forum (National), and have shared the testing options pack to every DPH. Additionally, [Name Redacted] presented to the East of England DPH Forum on 17/07, covering some upcoming localisation activities and how they can support. Further engagement is scheduled with DPHs from across the sub-regions of London (North East, North West, South East, South West) over the next two weeks. | Regional Engagement team has been introduced at the Fortnightly DPH Forum (National), and have shared the testing options pack to every DPH. Additionally, [Name Redacted] presented to the East of England DPH Forum on 17/07, covering some upcoming localisation activities and how they can support. Further engagement is scheduled with DPHs from across the sub-regions of London (North East, North West, South East, South West) over the next two weeks. | Regional Engagement team has been introduced at the Fortnightly DPH Forum (National), and have shared the testing options pack to every DPH. Additionally, [Name Redacted] presented to the East of England DPH Forum on 17/07, covering some upcoming localisation activities and how they can support. Further engagement is scheduled with DPHs from across the sub-regions of London (North East, North West, South East, South West) over the next two weeks. | Regional Engagement team has been introduced at the Fortnightly DPH Forum (National), and have shared the testing options pack to every DPH. Additionally, [Name Redacted] presented to the East of England DPH Forum on 17/07, covering some upcoming localisation activities and how they can support. Further engagement is scheduled with DPHs from across the sub-regions of London (North East, North West, South East, South West) over the next two weeks. | Regional Engagement team has been introduced at the Fortnightly DPH Forum (National), and have shared the testing options pack to every DPH. Additionally, [Name Redacted] presented to the East of England DPH Forum on 17/07, covering some upcoming localisation activities and how they can support. Further engagement is scheduled with DPHs from across the sub-regions of London (North East, North West, South East, South West) over the next two weeks. | Regional Engagement team has been introduced at the Fortnightly DPH Forum (National), and have shared the testing options pack to every DPH. Additionally, [Name Redacted] presented to the East of England DPH Forum on 17/07, covering some upcoming localisation activities and how they can support. Further engagement is scheduled with DPHs from across the sub-regions of London (North East, North West, South East, South West) over the next two weeks.
Local Authority Engagament
Regional Engagement Leads are working closely with Senior Regional Coordinators to discuss testing options with Local Authorities, and collect and communicate testing requirements back into the channels teams (e.g. LTS team, Satellites etc). In addition to this, the Regional Engagement Leads are focussed on understanding and collecting local needs and challenges that need to be addressed as part of the localisation roll-out, and are working with different aspects of the programme to report back and help solve these challenges (e.g. data collection and reporting).
Summary totals |  |  | Total number of authorities | 155 | (London categorised into Sub-Regions, plus DAs)
Total Authorities Engaged | 33 | 21.29%
Total discussions pending | 0 | 0%
No. of areas to be engaged | 0 | 0%
Regional breakdown
| East of England | East Midlands | West Midlands | London | North East | North West | South East | South West | Yorkshire & Humber
Number of authorities | 12 | 9 | 14 | 33 | 12 | 23 | 17 | 17 | 15
Total Authorities Engaged | #REF! | #REF! | #REF! | 33 | #REF! | #REF! | #REF! | #REF! | #REF!
Total discussions pending | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
No. of areas to be engaged | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
Total Authorities Engaged (percentage) | #REF! | #REF! | #REF! | 100% | #REF! | #REF! | #REF! | #REF! | #REF!
Total discussions pending (percentage) | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
No. of areas to be engaged (percentage) | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region.
The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region.
The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region.
The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region.
The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region.
The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region. | The Regional Engagement team is working closely with the Local Test Site team to identify potential and upcoming LTS sites, that form part of the pipeline. The process for how these teams work together has been documented and is currently in progress. Conversations are continuing alongside Senior Regional Coordinators across the region - there has been a changeover in SRCs in the Midlands. [Name Redacted] has followed up with [Name Redacted] (East Midlands) and [Name Redacted] (West Midlands), and regular sessions have now been set up to coordinate efforts across the region.