## CTM Checklist
Readiness Checklist for Cwm Taf Morgannwg University Health Board
Key |  | Criteria successfully met |  | Date of last update: | 2020-11-14
Criteria approaching compliance but concerns remain
|  | Criteria not met |  | Planned Go Live Date: | 2020-11-24
[14 empty] | Checkpoint Status | [13 empty] | Progress Comments
| Area | Critical Risk to Successful Delivery | Critical Date | Risk Assessment (Go/ No Go issue) | Lead | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01
ref | WAST Critical Issues
1 | Efficiency – Sickness Levels | Average monthly sickness levels are less than 6% to avoid impacting on staff available to roster (to include both nursing and call handlers) | 2019-09-01 | Yes (low risk if less than 8%; high risk if more than 10%) | Area manager NHSDW/ 111 | 6.35% | 6.8% | 7.54% | 6.64% | 7.56% | 7.13% | 10.08% | 7.95% | 8.3% | 7.3% | 7.3% | 8.93% | 10.11% | 8.75% | 7.95% | 8.08% | 15.6%* | 14.6%* | 10.1%* | 9.24% | 8.23% | 9.1% | 8.3%
2 | Performance | 111 Monthly abandonment rate is 5% or less. Overall | 2019-09-01 | Yes (high risk if higher than 10% on Sat & Sun throughout previous 3 months) | Area manager NHSDW/ 111 | 13.8% | 6.5% | 5% | 2.8% | 3.7% | 2.77% | 11.2% | 6.8% | 5.8% | 6.3% | 6.1% | 12.3% | 7.8% | 10.2% | 23.3% | 5.2% | 22.7% | 8.5% | 2.9% | 5.6% | 11.6% | 25.1% | 6.4% | Call demand: June 39.5k July 40.2k Aug 50.1k Sept 62.1k Oct 54.5k
3 |  | 111 Monthly abandonment rate for OOH period is 5% or less. Weekend | 2019-09-01 | Yes (high risk if higher than 10% on Sat & Sun throughout previous 3 months) | Area manager NHSDW/ 111 | 16% | 8.5% | 6.2% | 3.2% | 4.4% | 3% | 12.2% | 7.1% | 6.5% | 7.6% | 6.9% | 13.9% | 8.3% | 11% | 26.5% | 5.7% | 19.7% | 8.9% | 2.9% | 5% | 12.6% | 17.2% | 5.9% | Call demand: June 39.5k July 90.2k Aug 90.1k Sept 62.1k Oct 54.5k
4 | Productivity – call handling and nurse advisor AHT | Average handling times are within agreed levels - 650 secs for Call Handlers | 2019-09-01 | Yes (high risk if levels are 10% or more above these levels). | Area manager NHSDW/ 111 | 620 | 625 | 620 | 635 | 635 | 623 | 665 | 649 | 644 | 661 | 671 | 683 | 668 | 662 | 662 | 645 | 706 | 686 | 665 | 668 | 659 | 682 | 631
5 |  | Average handling times are within agreed levels - 900 secs for Nurse Advisors (within strategic plan) | 2019-09-01 | 1100 average over the last 2 years since going live (tolerance within range) | Area manager NHSDW/ 111 | 1195 | 1061 | 1125 | 1164 | 1117 | 1045 | 1089 | 1080 | 1153 | 1119 | 1063 | 1051 | 1107 | 1175 | 1067 | 1100 | 1133 | 1199 | 1174 | 1172 | 1198 | 1148 | 1144 | Bank contribution = 2.3wte
6 |  | Call flow to GPOOH should not exceed 60% of volume during OOH Period. | 2019-09-01 | Increased risk if call flow to GPOOH is above 60% with improvement trajectory needing to demonstrate reductions in volume | Area Manager NHSDW/ 111 | 60.01% | 59.13% | 57.6% | 55.63% | 55.6% | 57.38% | 57.1% | 56.7% | 55.9% | 54% | 54% | 57% | 56.1% | 55.9% | 56.2% | 52.5% | 51.8% | 51.5% | 49.8% | 48.8% | 51.9% | 51.6% | 52% | Call demand: June 39.5k July 00.2k Aug 50.1k Sept 649.1k Oct 54.5k
7 | Outcomes | Effectiveness of service in managing calls away from 999 to be maximised to avoid destabilisation of urgent care system. (using September 2017 position as a baseline 999 – 5.4%) | 2019-09-01 | Yes – high risk if current level of referral to 999 increases above baseline levels | Area manager NHSDW/ 111 | 5% | 4.9% | 5.7% | 6.6% | 5.6% | 6% | 6.4% | 6.9% | 6.5% | 6.4% | 6.3% | 7% | 7.2% | 7.2% | 6.6% | 7.1% | 4.9% | 5.5% | 6.1% | 6.3% | 5.4% | 4.9% | 6.8% | Call demand: June 39.5k July 80.2k Aug 50.1k Sept 66.1k Oct 54.5k
8 |  | Effectiveness of service in managing calls away from ED to be maximised to avoid destabilisation of urgent care system. (using September 2017 position as a baseline ED – 9.7%) | 2019-09-01 | Yes – high risk if current level of referral to ED increases above baseline levels | Area manager NHSDW/ 111 | 10.1% | 10.7% | 11.3% | 12.3% | 13.1% | 12.2% | 11.4% | 11.5% | 12.1% | 12.8% | 12.2% | 12.7% | 12.9% | 13.1% | 12.1% | 13.5% | 9% | 11.4% | 12.6% | 11.7% | 10.9% | 8.8% | 12.6% | Call demand: June 39.5k July 60.2k Aug 40.1k Sept 612.1k Oct 54.5k
9 | Workforce | Sufficient overall staff are in post to manage predicted demand in line with call flow model | 2019-09-01 | Yes – high risk if the establishment within 0845/111 is below 95%. | Area manager NHSDW/ 111 | N/A | N/A | N/A | 90% | 99% | 98% | 86.1% | 88.3% | 98.97% | 96.4% | 96.2% | 93.9% | 96% | 91.7% | 90.6% | 99% |  |  | 90.2% | 93.4% | 91.5% | 89.9% | 92.4% | Excludes x5 CH delayed training.
a |  | Sufficient Clinical staff are in post to manage predicted demand in line with call flow model | 2019-09-01 | Yes – high risk if the establishment within 0845/111 is below 95%. | Area manager NHSDW/ 111 | [6 empty] | 81.8% | 89.56% | 93.57% | 91.4% | 91.9% | 93.7% | 92.5% | 93.2% | 91.4% | 95.5% |  |  | 85% | 82% | 86.5% | 89.5% | 90% | Bank contribution = 5.3wte 5 x CA complete training 28 Dec
b |  | Sufficient Call Handling staff are in post to manage predicted demand in line with call flow model | 2019-09-01 | Yes – high risk if the establishment within 0845/111 is below 95%. | Area manager NHSDW/ 111 | [6 empty] | 90.7% | 87% | 105% | 102% | 101% | 95% | 94.6% | 92.8% | 91.1% | 96.8% |  |  | 93% | 88.3% | 96.1% | 90% | 94.5% | Bank contribution = 2.3wte Additional 22 CH complete training 30 Nov and further 18 complete by 28 Dec
10 |  | Rostering of available call handling and nursing staff is matched to demand profile for in and out of hours | 2019-09-01 | Yes (High risk if shift fill rate falls below 95% of demand defined staffing levels – unit hours production) | Area manager NHSDW/ 111 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep.
11 | Technical | Telephony infrastructure needs to be in place and tested ahead of service launch. | 2019-09-01 | Yes – callers must be able to access the service | WAST Head of ICT | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | 111 live in area due to Covid | 111 live in area due to Covid | 111 live in area due to Covid | 111 live in area due to Covid | 111 live in area due to Covid | 111 live in area due to Covid
12 |  | HB Border dialling issues resolved and tested. All HB patients accessing service | 2019-09-01 | Yes (High risk if confirmation not received) | WAST Head of ICT / HB Lead | N/A | N/A | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | 111 live in area due to Covid - dial plan for border patients agreed | 111 live in area due to Covid - dial plan for border patients agreed | 111 live in area due to Covid - dial plan for border patients agreed | 111 live in area due to Covid - dial plan for border patients agreed | 111 live in area due to Covid - dial plan for border patients agreed | Dial plan complete
13 |  | Technological connectivity to enable call flow must be established and tested prior to launch | 2019-09-01 | Yes – concentrator has to be fully operational otherwise service can’t launch | WAST Head of ICT |  |  | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Complete | Complete | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Connectivity testing commenced w/c 17th Aug - Ongoing | Connectivity testing commenced w/c 17th Aug - Ongoing | Connectivity testing Ongoing | Connectivity testing Ongoing - final testing scheduled for morning of go-live
ref | Health Board Critical Issues
14 | Information Technology | Adastra system should be robust and stable, and be at least version 3.16 to allow for concentrator functionality | 2019-08-01 | Yes – concentrator has to be in place otherwise service can’t launch. Assessed at least 5 months prior to launch. (Any upgrade to minimum version should be timetabled to be complete at least 12 weeks prior to launch to allow for concentrator testing) | Health Board Assistant Director of ICT | [6 empty] | testing undertaken without issues | Additional back up testing scheduled. | Concentrator testing being undertaken on early July - dates currently being confirmed | Concentrator testing complete in training environment - testing in live environment to be scheduled once known go live date | Concentrator testing complete in training environment - testing in live environment to be scheduled once known go live date | Concentrator testing complete in training environment - testing in live environment to be scheduled nearer to go live date date to be agreed with WAST colleagues | Concentrator testing complete in training environment - testing in live environment to be scheduled nearer to go live date date to be agreed with WAST colleagues | Concentrator testing complete in training environment - testing in live environment to be scheduled nearer to go live date date to be agreed with WAST colleagues | Concentrator testing complete in training environment - testing in live environment to be scheduled nearer to go live date date to be agreed with WAST colleagues | Concentrator testing complete in training environment - testing in live environment to be scheduled nearer to go live date date to be agreed with WAST colleagues | Concentrator testing complete in training environment - testing in live environment scheduled for Aug | Concentrator testing complete in training environment - testing in live environment scheduled for Aug | Concentrator testing complete in training environment - testing in live environment scheduled for Aug | Testing in live systems has been arranged for beginning of September | Due to technical mapping issues further testing is scheduled for week commencing 14th September | Connectivity testing Ongoing | Concentrator testing undertaken and mapping correctly - final testing on day of go-live
15 | Directory of Services | DOS needs to be robustly updated and tested against a checklist pre-launch to maximise opportunities to divert to alternative pathways | 2019-08-01 | Yes – medium risk if DOS not fully populated | HB Lead | Ongoing as part of roll out prep | Ongoing as part of roll out prep | Ongoing as part of roll out prep | Ongoing as part of roll out prep | Ongoing as part of roll out prep | Ongoing as part of roll out prep | routine maintenance from now | routine maintenance from now | DOS work near completion | DOS work near completion - clinical pathways refreshed | Dos work near completion - clinical pathways refreshed and completed - one or two outstanding dos entries | Dos work near completion - clinical pathways refreshed and completed - one or two outstanding dos entries | Dos work near completion - clinical pathways refreshed and completed - one or two outstanding dos entries | Dos work near completion - clinical pathways refreshed and completed - one or two outstanding dos entries | Dos work near completion - clinical pathways refreshed and completed - one or two outstanding dos entries | Dos work near completion - clinical pathways refreshed and completed - one or two outstanding dos entries | Dos work near completion - clinical pathways refreshed and completed - one or two outstanding dos entries | Dos work near completion - clinical pathways refreshed and completed - one or two outstanding dos entries | Dos work near completion - clinical pathways refreshed and completed - one or two outstanding dos entries | Dos work completed and submitted | Dos work completed and submitted | Dos work completed and submitted | Dos work completed and submitted
16 | Pathways | Critical alternative pathways need to be in place and tested against an agreed checklist pre-launch to maximise opportunities to divert from 999/ED. | 2019-08-01 | Yes – medium risk if pathways not in place | HB Lead | Ongoing as part of roll out prep | Ongoing as part of roll out prep | Ongoing as part of roll out prep | Ongoing as part of roll out prep | Ongoing as part of roll out prep | Ongoing as part of roll out prep | ongoing randomised testing of established pathways - continure to go live | ongoing randomised testing of established pathways - continure to go live | Clinical pathways completed | Clinical pathways completed | Clinical pathways completed | Clinical pathways completed | Clinical pathways completed | Clinical pathways completed | Clinical pathways completed | Clinical pathways completed | Clinical pathways completed | Clinical pathways completed | Clinical pathways completed | Clinical pathways completed | Clinical pathways completed | Clinical pathways completed | Clinical pathways completed
17 | Stability of GPOOH service | Capacity within GPOOH to cope with anticipated call flow from 111 with detailed modelling against 111 standards and revised demand assumptions – is the staffing sufficient to deliver the service. Shift fill rates for clinicians to be consistently maintained above 90% for 4 week period pre-launch. | 2019-08-01 | Yes – high risk if GPOOH doesn’t not have capacity to cope with incoming work. Assessment based on WG reported stats covering OOH period. | HB Lead | Shift Fill Average 78% | Shift Fill Average 78% | Shift Fill Average 78% | Shift Fill Average 78% | Recruitment of new GP's - taster session conversion rate to sessional approx 50%. | Forecasted shift fill rate approx 82% - ANP's in base mitigate base closures due to no GP | Although shift fill is low. There are plans in place to increase clinical capacity over time. If 111 modelling is reliable and reduces demand on OOHs service by anticipated 40% the service should be on course to meet anticipated demand Shift fill rate has been in mid 70s% for last three months. | Although shift fill is low. There are plans in place to increase clinical capacity over time. If 111 modelling is reliable and reduces demand on OOHs service by anticipated 40% the service should be on course to meet anticipated demand Shift fill rate has been in mid 70s% for last three months. | Although shift fill is low. There are plans in place to increase clinical capacity over time. If 111 modelling is reliable and reduces demand on OOHs service by anticipated 40% the service should be on course to meet anticipated demand Shift fill rate has been in mid 80s% for last three months. | Although shift fill is low. There are plans in place to increase clinical capacity over time. If 111 modelling is reliable and reduces demand on OOHs service by anticipated 40% the service should be on course to meet anticipated demand Shift fill rate has been in mid 80s% for last three months. | Although shift fill is low. There are plans in place to increase clinical capacity over time. If 111 modelling is reliable and reduces demand on OOHs service by anticipated 40% the service should be on course to meet anticipated demand Shift fill rate has been in mid 80s% for last three months. | Clinical capacity has increased with 25 new GPs taken on. Tender also will improve PCH position on weekends. shift fill above 80% | clinical capacity has increased with 25 new GPs taken on. Tender also will improve PCH position on weekends. shift fill above 80% | clinical capacity has increased with 25 new GPs taken on. Tender also will improve PCH position on weekends. shift fill above 90% | clinical capacity has increased with 25 new GPs taken on. Tender also will improve PCH position on weekends. shift fill above 90% | clinical capacity has increased with 25 new GPs taken on. Tender also will improve PCH position on weekends. shift fill above 90% | clinical capacity has increased with new GPs being recruited. Provision of weekend GPs at PCH fully established - Shift fill above 90% | clinical capacity has increased with new GPs being recruited. Provision of weekend GPs at PCH fully established - Shift fill above 90% | clinical capacity has increased with new GPs being recruited. Provision of weekend GPs at PCH fully established - Shift fill above 90% | clinical capacity has increased with new GPs being recruited. Provision of weekend GPs at PCH fully established - Shift fill above 90% | clinical capacity has increased with new GPs being recruited. Provision of weekend GPs at PCH fully established - Shift fill above 90% | clinical capacity has increased with new GPs being recruited. Provision of weekend GPs at PCH fully established - Shift fill above 90% | clinical capacity has increased with new GPs being recruited. Provision of weekend GPs at PCH fully established - Shift fill above 90%
18 | Call Flow | Professional line established tested and publicised pre-launch including paramedics and nursing homes | 2019-08-01 | Yes. Call flow and professional line in place as prerequisite for launch | HB Lead |  |  |  |  | # call handlers agreed | prof line arrangements confirmed | There are no changes planned to existing professional line |  | Call flow mapped and completed - professional line remains the same. | Call flow mapped and completed - professional line remains the same. | Call flow mapped and completed - professional line remains the same. | Call flow mapped and completed - professional line remains the same. | Call flow mapped and completed - professional line remains the same. | Call flow mapped and completed - professional line remains the same. | Call flow mapped and completed - professional line remains the same. | Call flow mapped and completed - professional line remains the same. | Call flow mapped and completed - professional line remains the same. | Call flow mapped and completed - professional line remains the same. | Call flow mapped and completed - professional line remains the same. | Call flow mapped and completed - professional line remains the same. | Call flow mapped and completed - professional line remains the same. | Call flow mapped and completed - professional line remains the same. | Call flow mapped and completed - professional line remains the same.
ref | Joint Requirements
19 | Escalation | Escalation plan and route agreed at least one month ahead of launch | 2019-08-01 | Yes | Area manager NHSDW/ HB Lead | [6 empty] | Feedback received from WAST. Plan amended and ready | Feedback received from WAST. Plan amended and ready | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Documents updated and will be uploaded into system on 17 Nov
20 | Business Continuity | BCI plan in place at least one month ahead of launch – deliver service model during periods of pressure, IT/telephony system failure or unforeseen significant event. | 2019-08-01 | Yes | Area manager NHSDW/ 111 & HB Lead | [6 empty] | Feedback received from WAST. Plan amended and ready | Feedback received from WAST. Plan amended and ready | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Documents updated and will be uploaded into system on 17 Nov
21 | Clinical Support Hub | Clinical Support Hub working effectively to manage flow with clear operational policies and processes in place between WAST CTM and SBUHB | 2019-08-01 | Yes | Programme Lead, HB Clinical Lead & Area manager NHSDW /111 | [6 empty] | Hub launched in Sept 2017 and is operational. | Hub launched in Sept 2017 and is operational. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. SOPS received from WAST. Need to identify GPs to work as part of HUB | Ongoing as part of roll out prep. SOPS received from WAST. Need to identify GPs to work as part of HUB | Ongoing as part of roll out prep. SOPS received from WAST. Need to identify GPs to work as part of HUB | Ongoing as part of roll out prep. SOPS received from WAST. Need to identify GPs to work as part of HUB | Ongoing as part of roll out prep. SOPS received from WAST. GP's identified to work as part of HUB | Ongoing as part of roll out prep. SOPS received from WAST. GP's identified to work as part of HUB | Ongoing as part of roll out prep. SOPS received from WAST. GP's identified to work as part of HUB | Work currently underway to configure Adastra Queues to allow CSH clinician to be able to access CTM Queues. Hub for CTM due to launch 20th Sept and there are sufficient GP's on rota | Work currently underway to configure Adastra Queues to allow CSH clinician to be able to access CTM Queues. Hub queue structure due to be tested w/c 20 Sept. Suffinet GP's on rota - rota finalised for launch | Work currently underway to configure Adastra Queues to allow CSH clinician to be able to access CTM Queues. Hub queue structure due to be tested w/c 20 Sept. Suffinet GP's on rota - rota finalised for launch | Adastra queues configured - CSH has been live for a numbe rof weeks - sufficient GPs available for launch
22 | Policies | Policies for management of interface and call flow all in place and agreed | 2019-09-01 | Yes | Programme Lead, HB Lead and Area manager NHSDW/ 111 | [6 empty] | HUB SOPS for streaming etc all shared. | HUB SOPS for streaming etc all shared. | Ongoing as part of roll out prep. | SOPS received from WAST | SOPS received from WAST | SOPS received from WAST | SOPS received from WAST | SOPS received from WAST | SOPS received from WAST | SOPS received from WAST | SOPS received from WAST | SOPS received from WAST | SOPS received from WAST | SOPS received from WAST | SOPS received from WAST | SOPS received from WAST | SOPS received from WAST
23 | Governance | Collaboration Agreement signed and agreed by respective Boards | 2019-09-01 | Yes | Programme Director, WAST and HB and Board Secretaries | [6 empty] | SE Wales CA in draft amended to include CTM. Pending approval | SE Wales CA in draft amended to include CTM. Pending approval | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | being revised with NWSSP awaiting updated document | being revised with NWSSP awaiting updated document | being revised with NWSSP awaiting updated document | being revised with NWSSP awaiting updated document | being revised with NWSSP awaiting updated document | being revised with NWSSP awaiting updated document | being revised with NWSSP awaiting updated document | final draft of document being submitted to 111 Board on 28th Aug | final draft of document being submitted to CTM 111 Board on 24th Sept | final draft of document being submitted to CTM 111 Board on 24th Sept | Final version discusserd with DOPC - ready for sign off
24 | Information Sharing | Information Sharing Protocol agreed and signed by Caldicott Guardian | 2019-09-01 | Yes | Programme Director, Information Governance Leads at WAST /HB | [6 empty] | ISP incorporated into SE Wales CA in draft . Pending approval | ISP incorporated into SE Wales CA in draft . Pending approval | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | being revised with NWSSP awaiting updated document | being revised with NWSSP awaiting updated document | being revised with NWSSP awaiting updated document | being revised with NWSSP awaiting updated document | being revised with NWSSP awaiting updated document | being revised with NWSSP awaiting updated document | final draft of document being submitted to 111 Board on 28th Aug | Submitted for signature 14th September | Submitted for signature 14th September
25 | Demand | Changes in the demand profile for 0845/111 and GPOOH exceed planning assumptions | 2019-08-01 | Yes – continual reassessment required throughout Jan-March 2019 and if more than 10% increase in activity requires re-evaluation. | Area manager NHSDW/ 111 & HB Lead | [6 empty] | not available yet | not available yet | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | Ongoing as part of roll out prep. | CTM demand for OOH up slightly for period apr -Dec 2019 around 8% will continue to be monitored - based on logged calls | CTM demand for OOH up slightly for period apr -Dec 2019 around 8% will continue to be monitored - based on logged calls | Detailed demand and capacity review completed - agreed an additional 11.83wte call handlers to meet overall increases in 111 demand | Detailed demand and capacity review completed - agreed an additional 11.83wte call handlers to meet overall increases in 111 demand | Detailed demand and capacity review completed - agreed an additional 11.83wte call handlers to meet overall increases in 111 demand | Detailed demand and capacity review completed - agreed an additional 11.83wte call handlers to meet overall increases in 111 demand | Detailed demand and capacity review completed - agreed an additional 11.83wte call handlers to meet overall increases in 111 demand. Recent demand and capacity modelling undertaken as a result of 38% increase in demand. 111 Programme have agreed to fund an additional 41wte call handlers | Recent demand and capacity undertaken - agreed an additional 41wte call handlers to meet demand profile | Recent demand and capacity undertaken - agreed an additional 41wte call handlers to meet demand profile